## Sheet1
CHNA Time line (tentative)
CHNA Key Components:
* Initial Needs Assessment representing baseline for future CHNAs
* Tracking of Community Benefit for each CHNA
* Implementation Plan for each CHNA Coordination/Collaboration related to planned interventions/services
* Annual Report to IRS and the public
Key Components | Sept. 2012 | Oct. 2012 | Nov. 2012 | Dec. 2012 | Jan. 2013 | Feb. 2013 | Mar. 2013 | Apr. 2013 | 2012-05-01 | Jun. 2013 | Jul. 2013 | Aug. 2013 | Sept. 2013 | Oct. 2013 | Nov. 2013 | Dec. 2013
Cmt. Mtgs. | CHNA mtg | CHNA mtg | CHNA mtg | CHNA mtg |  | CHNA mtg |  | CHNA mtg |  | CHNA mtg |  | CHNA mtg |  | CHNA mtg |  | CHNA mtg
Needs Assessmt |  |  |  |  | CHNA Indicators cofirmed |  |  | DRAFT CHNA Data Done | [5 empty] | Final CHNA Done |  | Adopt CHNA Imp. Plan
|  |  |  | meet w internal staff on inter. data | ,-------Data mining process--- |  |  | ,--rioritization Process
Comm. Benefit Tracking |  |  |  |  | ,-----Start tracking Comm. Benefits by each organization's CHNAs on an ongoing basis--- | [10 empty] | IRS report Due
Communications | Confirm Adv. Council makeup | 1st Adv. Council Wrkshop/ RHA mtg? | Present to Gov. Board & CEOs |  |  | Present to Gov. Board & CEOs |  |  | Present to Gov. Board & CEOs | 2nd Adv. Council Wrkshop/ RHA mtg |  | Present to Gov. Board & CEOs |  |  | Present to Gov. Board & CEOs | Publicize report
| ID internal staff at each org | [8 empty] | Council input on priorities
RHA-Coalition Partnerships |  | Present Indicators to council | [5 empty] | Start on Imp. Plan design |  |  | ,---Begin Imp. Plan work coord. Ongoing RHA work in communities---